## Dashboards
MESHNET: two dashboards
One backend serves both. Each has a different user and a different login.
| Admin dashboard | Phone app dashboard
Used by | You or the network operator | Each phone connected to MESHNET
Shows | All nodes, routes, gateway load, alerts, billing totals | This phone's status, route and hops, speed, data used, credit balance, earnings
Controls | Approve gateways, set price per MB and the split, data allowances, block abusive nodes | Share my connection on or off, data cap, battery limit, top up credit
Login | Admin username and password (not built yet) | The phone's signed identity (already built in Stage 2)
Current status | First draft built (the Stage 3 dashboard). Login and approve button not built. | Not built. Needs new endpoints, such as GET /api/me, that use the signed requests already in place.
Project folder | admin/ (today's frontend, plus login and approve button) | phone/ (new)

## Phone UI options
Options for the phone app dashboard
Relaying over Wi-Fi or Bluetooth in the background needs native Android code. A plain web page cannot do it.
# | Option | What it means | Recommended?
1 | React inside a native Android shell | A Kotlin service does the relaying and your React dashboard is the screen, so you reuse what you have learned. | Yes (recommended)
2 | React Native | Also JavaScript, but its components differ from the web React you have been using. | No
3 | Fully native Kotlin screens | Gives the best control but means learning two UI approaches. | No

## Build tracker
Build tracker
Change the Status column using the drop-down. The summary counts update automatically.
Summary
Built | 2
In progress | 0
Not started | 7
Decision needed | 1
Item | Dashboard | Status | Notes
Admin dashboard: first draft (nodes, routes, live updates) | Admin | Built | The Stage 3 dashboard
Admin login (username and password) | Admin | Not started
Approve-gateway button | Admin | Not started | Today approval works only through the API with the dev token
Price per MB and split settings | Admin | Not started
Data allowances and blocking abusive nodes | Admin | Not started
Phone identity (signed requests) | Phone | Built | Stage 2
GET /api/me endpoint (phone's own stats and balance) | Phone | Not started | Uses the existing signed requests
Choose phone UI approach (see Phone UI options) | Phone | Decision needed | Recommended: React inside a native Android shell
Phone app dashboard screens | Phone | Not started
Split project into admin/ and phone/ folders | Both | Not started